## Project Plan
Rice Disease Diagnostic System - Project Plan
Mwea case study ¦ CNN-based web app ¦ Steps in the order they need to be done
How to use: yellow cells are yours to edit. Pick a Status from the dropdown, enter a Target date (dd-mmm-yyyy) and any Notes. The progress figures below the table update automatically.
Ex. | Example step (ignore this row) | Shows the expected format for the yellow columns. |  |  | In progress | 2026-11-15 | Waiting for KALRO reply
# | Step | What to do | Output / evidence | Feeds report section | Status | Target date | Notes
1 | Decide the scope | Pick the 4-6 diseases you will cover and whether you are building a website or an Android app. Confirm the disease list with KALRO or the Mwea extension officers. | A short scope statement agreed with your supervisor | 1.6 Objectives, 1.8 Scope, 3.6 Implementation | In progress |  | Scope drafted (see Decisions sheet); waiting for your supervisor to agree.
2 | Get the data | Arrange labelled leaf photos in one folder per disease. Start with a public rice leaf dataset, then add photos from Mwea checked by an extension officer. | dataset/ folder with one sub-folder per class | 3.3 Data collection (dataset not yet named) | In progress |  | Six supported classes organized from local and Kaggle training data: 5,344 unique images; Kaggle validation kept separate (518 unique images). No Mwea field images or expert confirmations yet.
3 | Train and evaluate the model | Run the rice_cnn.py script on your dataset. Hold back photos the model never sees during training and score it on those. | Accuracy, precision, recall, confusion matrix, saved model | 3.5.6 Pseudo code, new Results chapter | Done |  | Six-class CNN trained for 5 epochs. Grouped internal test (799): accuracy 85.73%, macro precision/recall/F1 0.8427/0.8886/0.8556. Separate Kaggle validation (518): accuracy 72.39%, macro P/R/F1 0.7658/0.7222/0.7158. Reports and confusion matrices saved in model/. Dataset-only results; not Mwea field performance.
4 | Build the website | A simple page with an upload button that calls the trained model and shows the result. | Working web app (upload, diagnosis, confidence, history log) | 5.2 Proposed system, I/O design and mock-up screens | Done |  | Flask application now serves the six-class model; upload, prediction, confidence, history, health check, and 14 automated tests verified.
5 | Test it with real people | Farmers and extension officers try it: the questionnaires and interviews already promised in Chapter 3. | Feedback forms and test results | 3.3.3 Interviews, 3.3.4 Questionnaires, 3.7 Testing, Results chapter | Not started |  | Get permission and consent first.
6 | Finish the report | Write section 4.5 and the rest of Chapter 5, add the missing diagrams (Figures 3.1-3.5), a results chapter and a conclusion. | Complete report | 4.5, Chapter 5, Results chapter, Conclusion | In progress |  | Ask your supervisor which chapters are expected after Chapter 5.
Steps done
Steps in progress
Total steps
Progress (steps done)

## Status Tracker
Where You Stand
Statuses reflect the proposal document as I read it. Update them as you make progress.
Yellow cells are yours to edit. Pick a Status from the dropdown; the summary table below counts them automatically.
# | Item | Category | Status | Notes / next action
1 | Chapters 1-3 (Introduction, Literature review, Methodology) | Report | Done | Drafted, but contradictions still need fixing (web vs Android, binary vs multi-class, objectives).
2 | Chapter 4 (System analysis), sections 4.1-4.4 | Report | Done | Written; the chapter summary promised in 4.1 is still missing.
3 | Chapter 5 (System design), sections 5.1-5.2 | Report | Done | Written so far; the remaining sections are in the row 'Rest of Chapter 5'.
4 | Training script (rice_cnn.py) | System | Done | Training script creates reproducible grouped train/validation/test splits and separate external Kaggle evaluation; six-class reports and confusion matrices saved.
5 | Dataset | System | In progress | Six supported classes organized with provenance; Kaggle validation retained separately. Mwea field images and expert confirmations have not been collected.
6 | Trained model and results | System | Done | Six-class model saved and served. Internal test: 85.73% accuracy (799); separate Kaggle validation: 72.39% (518). Per-class recall is uneven; this is not evidence of Mwea generalization.
7 | The website | System | Done | Modular Flask app serves six classes; upload/prediction API, diagnosis pages, history, and automated tests are in place.
8 | Diagrams (Figures 3.1-3.5) | Report | Not started | The captions exist in the proposal, but the figures themselves are not included.
9 | Section 4.5 (current-system flowchart, context diagram, DFD) | Report | Not started
10 | Rest of Chapter 5 (requirement analysis, conceptual architecture, process logic, database design, input/output screens, summary) | Report | Not started
11 | Results chapter and conclusion | Report | Not started | Ask your supervisor which chapters your university expects after Chapter 5.
Summary
| Category | Done | In progress | Not started | Total
Report
System
All items

## Decisions
Decisions to Settle First
Settle these with your supervisor before building anything.
Yellow cells are yours to edit: write your final decision and mark whether your supervisor has agreed. The Recommendation column is my suggestion, not a requirement.
# | Decision | Options | Recommendation | Why | Your decision | Agreed with supervisor?
1 | Website or Android app? | Website (Flask + HTML/CSS/JS) or native Android app (Kotlin) | Website | Most chapters and the code already assume a website. The proposal contradicts itself: the abstract and Chapters 4-5 say website, but section 3.6 says Android. | Website (Flask + HTML/CSS/JS) | Pending
2 | Which diseases to cover? | 4-6 diseases plus healthy | 4-6 diseases confirmed with KALRO or Mwea extension officers | Keeps the dataset and model manageable, and makes it a genuine Mwea case study. | Healthy, blast, brown spot, bacterial leaf blight, leaf scald, and narrow brown spot. RYMV remains future work until labelled RYMV data is provided. | Pending
3 | Keep the offline claim? | Keep it, drop it, or move it to future work | Drop it, or mention it as future work | A website needs internet, and section 5.2.3 already admits this, so the claim contradicts the design. | Dropped; listed as future work | Pending
4 | Drones, IoT sensors, voice control, explainable AI, farmer-knowledge integration | Keep, cut, or move to future work | Cut them or move them to 'future work' | None of it is realistic for one student or needed for the core system, and you can be marked down for promising things you did not build. | Moved to future work | Pending

## How It Works
What the System Does
The core of the project, in plain language.
# | Step | What happens
1 | Upload | The farmer photographs a rice leaf and uploads it through the website.
2 | Resize | The photo is resized so the CNN can read it.
3 | Classify | The CNN looks at the photo and returns a disease name with a confidence percentage.
4 | Save | The result is saved to a history log.
How the CNN learns
Think of it like teaching a child with flashcards: you show thousands of labelled photos ('this is blast, this is healthy') and it learns what each looks like.
# | Stage | What happens
1 | Train | Show the model thousands of labelled photos, one folder per disease.
2 | Hold back | Keep some photos the model never sees during learning.
3 | Score | Its score on those unseen photos is your accuracy figure.

## Photo Log
Mwea Photo Log
One row per photo. Class names match the folder names used by rice_cnn.py.
How to use: yellow cells are yours to edit. Log each photo as you take it. Pick the Class from the dropdown, and give every photo of the same plant the same Plant ID so they can be kept in one train/test split. Confirmed by = the extension officer or expert who verified the diagnosis. The summary on the right updates automatically.
Collection progress
# | File name | Class | Date taken | Mwea section / block | Rice variety | Growth stage | Plant ID | Confirmed by | Notes | Class | Collected | Target | % of target
Ex. | mwea_0001.jpg | blast | 2026-10-12 | Section 2, Block 14 | Basmati 370 | Tillering | P001 | J. Mwangi (extension officer) | Example row - ignore | healthy |  | 300
1 | [9 empty] | blast |  | 300
2 | [9 empty] | brown_spot |  | 300
3 | [9 empty] | bacterial_leaf_blight |  | 300
4 | [9 empty] | leaf_scald |  | 300
5 | [9 empty] | narrow_brown_spot |  | 300
6 | [9 empty] | Total
7 | [9 empty] | Assumption: a target of 300 photos per class is a rule of thumb, not a requirement. Agree the real target with your supervisor (blue cells).
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200